## Chapter Roadmap
Chapter | Task | Start Date | End State | Count
Clinical Management | Continuous Staff Cross Training for Different Areas and Staffing Contingency Plans | Month 0 | End
Clinical Management | Hold System-wide Leadership Safety Meetings | Month 0 | End
Clinical Management | Centralize Distribution of Supplies | Month 0 | End
Clinical Management | Send Weekly 'Need to Know' Emails from Leadership to all Employees | Month 0 | End
Clinical Management | Incorporate Telemedicine into Patient Care | Month 0 | End
Clinical Management | Designated Forums for Staff Support and Wellness Resources | Month 0 | End
RADx Process | Inception through POCTRN | Month 0 | Month 5.5
Surveillance & Initial Response | Evaluate Clinical Manifestations | Month 0 | Month 2
Surveillance & Initial Response | Monitor Symptomatology and Build Database | Month 0 | Month 2
Surveillance & Initial Response | Preliminary Evaluations of Available Data | Month 0 | Month 2
Surveillance & Initial Response | Notify Health Authorities (Local, National, International) | Month 0 | Month 2
Surveillance & Initial Response | Isolate and Identify Unknown Virus | Month 0 | Month 3
Surveillance & Initial Response | Promote and Implement Sanitary Measures for Disease Control | Month 0 | End
Surveillance & Initial Response | Maintain Surveillance Systems to Evaluate Severity of Outbreak and Health Impact | Month 0 | End
Variants | Establish Data Sharing and Analysis Platforms for Genome Sequence Data | Month 0 | Month 1
Surveillance & Initial Response | Identification of Human-to-Human Transmission | Month 1 | Month 3
Variants | Set Up Infrastructure and Protocols for Pathogen Genome Sequencing | Month 1 | Month 2
Variants | Create a Specimen Bank | Month 1 | Month 2
Variants | Acquire Samples, Sequence Pathogen Genomes, and Share Data | Month 1 | End
Verification & Validation | Patient Recruitment | Month 10 | Month 10.5
Verification & Validation | Data Collection | Month 10 | Month 10.5
Regulatory | Provide Data on Test Performance with New Variants | Month 10.25 | End
Regulatory | Answer FDA Questions Regarding Submission | Month 10.5 | Month 10.75
Verification & Validation | Analysis | Month 10.5 | Month 10.75
Verification & Validation | Reporting | Month 10.5 | Month 10.75
Regulatory | Submit EUA | Month 10.75 | Month 11.25
Regulatory | Receive EUA | Month 11.25 | Month 11.5
Regulatory | Begin Transition to Full Approval | Month 11.25 | End
Clinical Management | Develop and Implement Tiered Vaccination Plan | Month 11.5 | End
Societal Involvement | Require Vaccination for Return to Work/School | Month 12 | End
Societal Involvement | Prioritize Vaccination of Essential Workers | Month 12 | End
Commercialization | Diagnostic Kit Shipment | Month 13 | Month 24
Surveillance & Initial Response | Assessment of Disease Infectivity & Transmissibility | Month 2 | Month 4
Commercialization | Market Research & Intelligence Gathering | Month 3 | Month 24
Commercialization | Digital Infrastructure R&D | Month 3 | End
Immunology | Define Viral Load During Disease Progression | Month 3 | Month 4
Immunology | Define Humoral Response During Disease Progression | Month 3 | Month 5
Immunology | Asses Pre-existing Immunity | Month 3 | End
Quality & Risk Management | Gap Analysis (Understand Team and Product Maturity) | Month 3 | Month 3.25
Quality & Risk Management | Implement Electronic Document Management Tool | Month 3 | Month 3.5
Quality & Risk Management | Publish Document Control and Records Management Process | Month 3 | Month 3.5
Societal Involvement | Public Health Communication through Trusted Local Voices | Month 3 | End
Societal Involvement | Implement Protective Measures Based on Behavioral Science | Month 3 | End
Societal Involvement | Increase Access to Mental Health Care | Month 3 | End
Societal Involvement | Prioritize Essential Workers and Low-Income Communities | Month 3 | End
Societal Involvement | Support Remote Learning for Low-Income Students | Month 3 | Month 5.75
Clinical Management | Implementation of a Standardized Incident Response System | Month 3.25 | Month 3.75
Diagnostics | User Type Identification (POC, OTC, Lab) | Month 3.25 | Month 3.5
Quality & Risk Management | Create Lightweight Product Realization Plan | Month 3.25 | Month 3.5
Clinical Management | Prioritize Patient Care Needs and Adapt Operations | Month 3.5 | Month 3.8
Clinical Management | Evaluate and Re-design Throughput for ED and Other Unit | Month 3.5 | Month 4
Clinical Management | Create and Implement Plan to Manage Incoming Donations | Month 3.5 | Month 5.5
Diagnostics | Assay Target Selection | Month 3.5 | Month 3.75
Quality & Risk Management | Develop Laboratory Practices, Processes, and Infrastructure | Month 3.5 | Month 4
Quality & Risk Management | Publish Lightweight Equipment and Material Management Practices | Month 3.5 | Month 4
Diagnostics | Sample Type Identification | Month 3.65 | Month 3.9
Clinical Management | Develop and Operationalize In-Hospital Diagnostic Testing | Month 3.75 | End
Diagnostics | Detection Modality Selection | Month 3.75 | Month 4.25
Clinical Management | Adapt and Restrict Visitor Policies | Month 3.8 | Month 11
Diagnostics | Pre-Validation Testing | Month 3.8 | Month 5.5
Diagnostics | Performance Review | Month 3.9 | Month 7
Diagnostics | Hardware Designation | Month 3.9 | Month 4.6
Clinical Management | Overhaul Non-patient Care Areas into Patient Care Areas | Month 4 | Month 10
Clinical Management | Contingency Plans for Expanded Morgue Needs | Month 4 | Month 6
Diagnostics | User Interface Creation | Month 4 | Month 4.7
Immunology | Determine Cellular Immune Response During Disease Progression | Month 4 | Month 6
Immunology | Determine Vaccine Immune Response | Month 4 | Month 8.25
Immunology | Develop Serological Assay | Month 4 | Month 8
Quality & Risk Management | Confirm Regulatory Compliance Strategy for Product | Month 4 | Month 4.5
Quality & Risk Management | Conduct Preliminary Risk Analysis | Month 4 | Month 5
Quality & Risk Management | Develop Risk Management Processes | Month 4 | Month 5
Societal Involvement | Mandate Masks Based on Disease Spread | Month 4 | Month 19.75
Clinical Management | Develop and Implement Plan for Monitoring of Discharged Patients | Month 4.25 | End
Diagnostics | Assay Optimization (Turnaround Time, Performance, Workflow, etc.) | Month 4.25 | Month 5.5
Clinical Management | Conserve PPE by Developing Geographic-based Model & Safe Storage for Reuse of Masks | Month 4.35 | End
Quality & Risk Management | Implement Initial Internal Feedback Infrastructure | Month 4.5 | Month 5
Diagnostics | Initial Testing (Buffer, Clinical Specimens, Spiked Matrix) | Month 4.6 | Month 5.8
Diagnostics | Selection of Assays Controls | Month 4.6 | Month 5.1
Diagnostics | Integration of Connectivity | Month 4.7 | Month 5.25
Diagnostics | Sample Procurement | Month 4.9 | Month 7
Commercialization | Portfolio Education and Training | Month 5 | Month 16
Commercialization | Market Price Sensitivity & Cost/Benefit Analyses | Month 5 | Month 17
Quality & Risk Management | Develop Product Testing, V&V, and Clinical Testing Processes | Month 5 | Month 5.5
Quality & Risk Management | Finalize Product Development | Month 5 | Month 6
Quality & Risk Management | Publish Device Master (DMR) Processes | Month 5.5 | Month 6
RADx Process | National Call for Innovative Technologies | Month 5.5 | Month 7.25
Diagnostics | Comparator Testing | Month 5.75 | Month 6.25
RADx Process | Rolling Submissions | Month 5.75 | Month 7.5
Commercialization | Investor Forum | Month 6 | Month 9
Commercialization | Business Operations Support | Month 6 | End
Immunology | Assess Natural and Vaccine Immune Response to Variants | Month 6 | End
Immunology | Investigate Plasma Therapy as a Therapeutic | Month 6 | End
Immunology | Assess Immune Response in Asymptomatic Patients | Month 6 | Month 10
Quality & Risk Management | Finalize Product Transfer to Manufacturing | Month 6 | Month 8
RADx Process | Viability Panel | Month 6 | Month 6.25
Societal Involvement | Support Summer Education for Low-Income Communities | Month 6 | Month 8.75 | Month 15 | Month 17
Societal Involvement | Plan for Return to In-Person Education | Month 6 | Month 8.75
Variants | Identification of a New Variant | Month 6 | Month 7
Variants | Perform In Silico Analysis of Existing Diagnostic Assays to Detect the New Variants | Month 6 | Month 7
Variants | Create Sample Pools for Testing Existing Diagnostic Assays to Detect the New Variant | Month 6 | Month 7
Variants | Perform Wet Lab Testing of Diagnostic Assays to Detect the New Variant | Month 6 | Month 8
Variants | Conduct Clear Public Communication (Variant Properties and Planned Mitigation Measures) | Month 6 | Month 7
Regulatory | Identify Desired Regulatory Claims | Month 6.20 | Month 6.6
Clinical Management | Explore Experimental Methods of Treatment | Month 6.25 | Month 7.25
RADx Process | Phase 0: "Shark Tank" - Like Rapid Selection Process | Month 6.25 | Month 6.5
RADx Process | Steering Panel | Month 6.5 | Month 6.75 | Month 7.75 | Month 8
RADx Process | Phase 1: Validation and Risk Review | Month 6.75 | Month 7.75
Resource Deployment | Collaborate with RADx Team to Perform a Project Resource Needs Evaluation | Month 6.75 | Month 7.5 | Month 8 | Month 8.75
Resource Deployment | Project Heat Map Management & Spending Data Monitoring | Month 6.75 | Month 23
Resource Deployment | *Vet External Vendors & Onboarding | Month 6.75 | Month 23
Resource Deployment | *Coordinate Sample Procurement | Month 6.75 | Month 23
Commercialization | Playbook Development and Dissemination | Month 7 | Month 11
Commercialization | Market Education & Roundtables | Month 7 | Month 10
Verification & Validation | Verification | Month 7 | Month 8.25
Verification & Validation | Cross Reactivity Studies | Month 7 | Month 7.5
Verification & Validation | Specificity Studies | Month 7 | Month 7.5
Verification & Validation | Written Documentation | Month 7 | Month 8.25
Resource Deployment | *Deploy Three Key Resources: Project Managers, QMS, and Regulatory | Month 7.25 | Month 8
Verification & Validation | Limit of Detection Testing | Month 7.5 | Month 8.25
Regulatory | Write Protocols for Required Testing | Month 7.9 | Month 8.4
Commercialization | Scale Up | Month 8 | End
Commercialization | Commercial Matchmaking/Business Development Support | Month 8 | End
Quality & Risk Management | Implement Tools to Manage Customer Feedback/Complaint/Adverse Events | Month 8 | Month 8.5
Quality & Risk Management | Publish Customer Feedback/Complaint/Adverse Event Reporting Processes | Month 8 | Month 8.5
RADx Process | Phase 2: Clinical Tests, Regulatory Approval, and Scaling Up | Month 8 | Month 23
Resource Deployment | Manage Resource Engagement | Month 8 | Month 23
Resource Deployment | Provide Additional Resources as Needed | Month 8 | Month 23
Resource Deployment | *Manufacturing Team Engaged | Month 8 | Month 23
Resource Deployment | *Supply Chain/Procurement Team Engaged | Month 8 | Month 23
Resource Deployment | *Supply Chain Forecasting | Month 8 | Month 23
Verification & Validation | Clinical Validation | Month 8.25 | Month 10.75
Verification & Validation | Site Selection | Month 8.25 | Month 10
Verification & Validation | IRB Approval | Month 8.25 | Month 10
Verification & Validation | Staffing and Training Clinical Site | Month 8.25 | Month 10
Verification & Validation | Define Inclusion and Exclusion Parameters | Month 8.25 | Month 10
Regulatory | Begin Draft of EUA Submission | Month 8.4 | Month 8.8
Quality & Risk Management | Implement Remaining QMS Modules and Deferred Tasks | Month 8.5 | End
Regulatory | RADx Regulatory Review of EUA Submission | Month 8.7 | Month 10.5
Societal Involvement | Support Safe In-Person Learning | Month 9 | End
Societal Involvement | Support for Remote Learning for Quarantined Low-Income Students | Month 9 | End
Societal Involvement | Mandate Screening Testing for Schools | Month 9 | Month 17
Variants | Perform Epitope Mapping to Identify Regions Targeted by the New Antigen Diagnostic Assay | Month 9 | Month 10
Variants | Perform In Silico Analysis to Assess Whether New Assays Detect Existing Variants | Month 9 | Month 10
Variants | Conduct Wet Lab Testing to Assess Whether New Assays Whether the New Diagnostic Assays Detect Existing Variants | Month 9 | Month 10
Variants | Investigate Patterns of Variant Evolution to Better Predict Future Variants | Month 9 | End
Regulatory | Incorporate Clinical Data into EUA Submission | Month 9.75 | Month 10.25